## Read Me
DRIMS × OpenSPP Fit/Gap Matrix
How to use:
1) In the 'Requirements' sheet, fill the blue columns (OpenSPP feature/module, support status, approach, gap notes, dependencies, status, owner).
2) Use 'Data Model' to map DRIMS entities/tables to OpenSPP data objects (or note gaps).
3) Use 'Dashboard' to validate each widget/report and note how it will be implemented.
4) 'Out of Scope - Later' tracks exclusions and Phase 2/Future items.
Tip: filter 'OpenSPP support?' = 'No' or 'Partial' to get a quick customization backlog.
Source document: Project Scope Statement 10.12.2025 (DRIMS).

## Requirements
Req ID | Spec Area | Requirement (from scope) | Priority | Source (section/page) | OpenSPP feature/module | OpenSPP support? | OpenSPP Solution | Approach | Customization / Gap notes | Dependencies / Integrations | Acceptance criteria (draft) | Status | Owner / Notes | Configuration Details | Open Questions
OBJ-01 | Objectives | Maintain a centralized, real-time inventory of all relief goods and services (donors, government, NGOs, other sources). | MVP | 2.a / p1 | spp_drims + stock | Yes | OpenSPP provides centralized inventory via Odoo's stock module integrated with DRIMS: • All relief items tracked in stock.quant with real-time quantities • DRIMS warehouses marked with is_drims_warehouse flag • Donations create stock receipts; requests create dispatch pickings • Stock On Hand menu shows consolidated view across all DRIMS warehouses • Multi-warehouse support with location hierarchy | Configure | Odoo stock module + DRIMS donations/requests provide centralized inventory with real-time updates | stock, spp_hazard | Inventory list updates in real-time across locations/users. | Models Ready |  | 1. Enable is_drims_warehouse on stock.warehouse records 2. Link warehouses to incidents via incident_ids M2M 3. Configure product categories for relief items 4. Set up donation source types in spp.vocabulary.code MISSING: Demo products, product categories. Warehouses defined (11 SL warehouses). | What is the expected update frequency for 'real-time'? Stock updates are immediate on transaction commit. Need to create product catalog (food, non-food, medical). What product categories for SL?
OBJ-02 | Objectives | Provide visibility of available resources and deployed government personnel/teams across disaster-affected areas. | MVP | 2.b / p1 | spp_drims + spp_area + spp_service_points | Partial | OpenSPP tracks resources via stock.quant and locations via spp_area: • Warehouse stock visible per location/product/lot • Service points (spp_service_points) track distribution locations • Agencies stored as res.partner with area linkage • Personnel visibility requires extension (teams not modeled) • GIS mapping available via spp_gis but requires integration | Extend/Customize | Service points track locations; personnel tracking needs spp_drims_sl agency data. Team deployment view needs dashboard enhancement. | spp_service_points, spp_area | Leaders can see resources + deployments by area. | In analysis | 2025-12-29: Updated config details — no is_agency field in code; use res.partner + partner categories/tags and spp_area area_id. | 1. Create agencies as res.partner (is_company=True) and load baseline list via spp_drims_sl/data/agencies.xml 2. Tag agencies by type using res.partner.category (Gov/NGO/Military/etc.) 3. Configure service points for distribution locations (spp_service_points) 4. Link personnel (res.users) to agencies (res.partner) and areas (spp.area) 5. Set up drims_area_ids on users for jurisdiction (record rules) | How should 'deployed teams' be modeled? As res.users groups, separate model, or service points? Is real-time GPS tracking of personnel required?
OBJ-03 | Objectives | Enable authorized field officers/agencies to request required goods/services through the system. | MVP | 2.c / p1 | spp_drims.request + spp_approval | Yes | spp.drims.request model enables field officer requests: • Online request form with product lines, quantities, priority • Destination area selection from spp_area hierarchy • Justification and affected population fields • Multi-tier approval via spp_approval with CEL-based routing • Request states: draft → pending → approved/rejected → dispatched → delivered | Configure | Request model with multi-tier approval workflow via spp_approval mixin. Field officers can submit requests linked to incidents. | spp_approval, spp_cel_domain | Authorized users can submit requests that enter approval workflow. | Models Ready |  | 1. Assign users to spp_drims.group_drims_officer 2. Configure approval workflow rules in spp_approval 3. Set CEL expressions for routing (e.g., total_value > 100000) 4. Define priority vocabulary codes (life_threatening, urgent, routine) MISSING: Demo incident to test full workflow. | Need sample incident with geographic area for realistic demo.
OBJ-04 | Objectives | Track issued, distributed, consumed, returned, or reused items end-to-end. | MVP | 2.d / p1 | spp_drims + stock | Yes | Full traceability via linked Odoo records: • Donation → donation_line → stock.move (receipt) • Request → request_line → stock.picking (dispatch) • Distribution tracked via picking completion + beneficiary fields • Returns via spp.drims.return with condition assessment • All movements audited via spp_audit with user/timestamp | Configure | Full traceability: Donation → Warehouse → Request → Picking (dispatch) → Distribution → Return. All with timestamps and user tracking. | stock, spp_audit | Each item movement is traceable with timestamps and actors. | Models Ready | 2025-12-29: Clarified configuration — spp_studio_drims exists but is not integrated into spp_drims alert engine by default. | 1. Create spp.hazard.incident records for each disaster 2. Link warehouses to incidents 3. Alert thresholds are configurable via DRIMS → Configuration → Alert Settings (spp_studio_drims provides UI, spp_drims owns parameters) 4. Set up user default incident (drims_default_incident_id) MISSING: Demo donations and dispatches to show traceability. | What admin levels are needed? National dashboard vs provincial vs district filtering is supported via spp_area hierarchy. Create demo scenario: donation received → stored → requested → dispatched?
OBJ-05 | Objectives | Provide unified dashboard (national/provincial/district) with real-time stock, distribution status, and pending requests. | MVP | 2.e / p1 | spp_drims dashboard + spp_hazard (spp.hazard.incident) | Partial | Incident-based dashboard with KPI stat buttons: • drims_donation_count/value, drims_request_count/pending • drims_stock_value, drims_distributed_value, drims_return_count • Kanban view of active incidents with status badges • Graph views: donation trend (line), request status (pie) • Missing: stock by category chart, GIS map, beneficiary aggregation | Configure | Dashboard on incident with KPI stat buttons implemented. MISSING: beneficiaries_served_30d, stock_by_category chart, map view. Alert integration done. | spp_hazard, spp_area | Dashboard reflects real-time data with filters by admin level. | In build | 2025-12-29: Added Open Question to clarify remaining scope/acceptance. 2025-12-29: Clarified feature reference — hazard incident model is spp.hazard.incident (module spp_hazard), not spp_hazard.incident. |  | Confirm required dashboard granularity: national/provincial/district views and how they should be secured (record rules vs separate menus).
IM-01 | Inventory Management | Receive and register all incoming relief goods/services capturing donor/source, date, quantity; expiry date for consumables. | MVP | 3.1.a / p1 | spp_drims.donation + donation.line | Yes | Donation registration via spp.drims.donation: • Donor tracking (res.partner with donation_source_type_id) • Full state workflow: announced → received → inspected → stocked/rejected • All transition buttons: Mark Received, Mark Inspected, Stock Items, Reject, Cancel • Partial receipt handling: quantity_pledged vs quantity_received with variance display • Stock creation on stocking (via stock.picking linked to donation) • Line-by-line condition assessment with vocabulary codes • Kanban view for visual state tracking with drag-drop • Receipt variance indicator on donation form | Configure | Donation model captures donor, source type, date, warehouse. Lines capture product, qty, condition, expiry date for consumables. | stock | Users can record receipts with required fields; consumables require expiry date. | Models Ready |  | 1. Configure donation source types vocabulary (government, ngo, private, international) 2. Configure item conditions vocabulary (new, used, damaged) 3. Set up warehouse receiving locations 4. Configure product categories with is_consumable flags NEEDED: Sample donations with line items. Warehouses exist. | Is expiry date mandatory only for consumables or all items? Currently optional field on donation line. Create demo donations from NGOs/government agencies?
IM-02 | Inventory Management | Categorize items (food, water, medicine, hygiene, shelter, equipment, non-consumables, etc.). | MVP | 3.1.b / p1 | product.category (Odoo core) | Yes | Standard Odoo product.category hierarchy: • Pre-defined categories: Food, Water, Medicine, Shelter, Hygiene, Equipment • Unlimited sub-category nesting • Products linked to category via categ_id • Category-based filtering in all stock views • spp_drims_sl_demo provides SL-specific category tree | Configure | Standard Odoo product categories. spp_drims_sl preloads: Food, Water, Medicine, Shelter, Hygiene, Equipment categories. |  | Items are assigned to categories and reports can group by category. | Models Ready |  | 1. Product categories created in spp_drims_sl/data/product_categories.xml: - Food (Dry Rations, Cooked Meals, Infant Food) - Water - Medical Supplies (Medicines, First Aid, Equipment) - Hygiene (Personal, Cleaning) - Shelter (Tents, Bedding, Materials) - Clothing - Equipment (Power/Lighting, Rescue, Communication, Tools) - Kitchen 2. Categories use product.category with hierarchical structure 3. Automatically loaded on module install | Exact category tree: Food > Dry Rations, Fresh Food, etc.?
IM-03 | Inventory Management | Unique identification / barcode / QR code generation for physical tracking (optional). | Phase 2 | 3.1.c / p1 | product.product (Odoo core) + stock.lot | Partial | Odoo barcode support on products and lots: • barcode field on product.product and stock.lot • Barcode nomenclature configuration • PDF reports can include barcodes (Code128, QR) • Mobile scanning requires Odoo Enterprise or Phase 2 custom app • Waybill reports can include item barcodes | Extend/Customize | Odoo supports barcode/QR on products and lots. Can generate via reports. Phase 2 for mobile scanning. | product_expiry | System can generate/print/assign barcodes or QR codes to item batches/units. | In analysis |  | 1. Enable barcode field on product.product 2. Configure barcode nomenclature in Odoo settings 3. Set up report template for barcode/QR printing 4. (Phase 2) Mobile scanning requires spp_mobile or PWA integration | Is batch-level or unit-level tracking required? stock.lot supports lot-level barcodes. What barcode format? EAN-13, Code128, QR?
IM-04 | Inventory Management | Real-time stock updates for additions, issues, returns, write-offs. | MVP | 3.1.d / p1 | stock.quant (Odoo core) | Yes | Real-time updates via Odoo stock transactions: • Donation stocking creates inbound picking → stock.move → stock.quant update • Request dispatch creates outbound picking → stock reduction • Returns create inbound moves to restock/quarantine/dispose locations • Inter-warehouse transfer wizard with incident tracking • Stock adjustment wizard for damage/loss/theft/expired/counting errors • All movements linked to incident via drims_type_id • Audit trail via spp_audit module | Configure | Real-time stock via Odoo stock_quant. DRIMS triggers stock updates on donation receive, request dispatch, returns. | stock | Stock balances update immediately after each transaction type. | Models Ready |  | 1. NEW: DRIMS → Inventory → Stock On Hand menu (action_drims_stock_quant) 2. Filtered to DRIMS warehouses automatically 3. Group by warehouse, product category 4. Export to Excel supported 5. Stock updates automatically on donation receive/request dispatch
PA-01 | Personnel & Agencies | Directory of agencies, response teams, and deployed personnel incl. location, contact, role, jurisdiction. | MVP | 3.2.a / p1 | res.partner (agencies) + spp_service_points + spp_drims_sl | Yes | Personnel tracked in spp.drims.personnel: • Linked to user, organization, incident, and deployment area • Status workflow: standby → deployed → on_leave → returned • All status transition buttons in form view (Deploy, Standby, On Leave, Return) • Calendar view for deployment visualization (date ranges by status) • Role assignment via vocabulary codes • Area-based record rules for visibility • Smart buttons: deployment history count | Extend/Customize | Agencies in res.partner with is_agency flag. Service points for locations. spp_drims_sl preloads SL agencies. Personnel directory needs enhancement. | spp_service_points | Directory supports search/filter; each record stores required fields. | Models Ready |  | 1. Create res.partner records with is_agency=True (or custom field) 2. Link agencies to spp.area for jurisdiction 3. Add contact fields: phone, email, emergency_contact 4. spp_drims_sl preloads DMC, MOH, Police, Military agencies | Should personnel be linked to agencies? What fields needed for personnel beyond standard res.users?
PA-02 | Personnel & Agencies | Geo-mapping of deployed teams/agencies (optional, if integrated with GIS). | Future | 3.2.b / p1 | spp_gis + spp_area + res.partner | Partial | GIS capabilities via spp_gis module (requires integration): • PostGIS backend for geo-queries • Map views and data layers supported • GPS coordinates on stock.picking for POD location • Phase 2: Add warehouse/agency geo layers • Phase 2: Real-time team location tracking | Extend/Customize | GPS lat/lng fields exist on stock.picking for POD location. spp_gis module available but NOT integrated with DRIMS warehouses/incidents. Need to create GIS data layers. | spp_gis, spp_area | Map view shows teams/agencies by location when GIS is available. | In analysis |  | 1. Install spp_gis module 2. Add geo coordinates to agencies (via area_id or direct lat/lng fields) 3. Create GIS data layer for agencies/teams 4. Configure map view with appropriate zoom level and base layer | What map base layer preferred? OpenStreetMap, Google Maps, custom? Should teams have real-time location updates or static deployment locations? CONFIRM: Is spp_gis a dependency for DRIMS? Currently not in depends list.
WF-01 | Request & Approval Workflow | Online submission of goods/service requests by authorized field officers/agencies. | MVP | 3.3.a / p1 | spp_drims.request | Yes | Request submission via spp.drims.request: • Field officers create requests with product lines • Incident and destination area linkage • Priority levels with SLA thresholds (critical 4h, high 8h, routine 24h, low 48h) • Request from Template wizard with quantity adjustment • Draft → Submit workflow with validation • Source warehouse selection after approval • Allocation preview wizard before FEFO allocation • Create Dispatch action generates stock.picking • Full audit trail with mail.thread | Configure | Request form with item lines, quantities, priority, justification, destination area, service point, affected population. | spp_approval | Request form supports item lines, quantities, priority and justification. | Models Ready |  | 1. Configure request priority vocabulary (life_threatening, urgent, high, medium, low) 2. Set up service points as destination options 3. Configure product list for requestable items 4. Set required fields validation (justification, affected_population) NEEDED: Demo incident + sample requests.
WF-02 | Request & Approval Workflow | Multi-level approval workflow (field → district → provincial/national as applicable). | MVP | 3.3.b / p1 | spp_approval (multi-tier) | Yes | spp_approval mixin for multi-tier workflows: • CEL expression-based routing rules • Approval thresholds by value, quantity, or custom criteria • Approve/reject/partial approve actions • Approval history and audit trail • Email notifications on state changes | Configure | Multi-tier approval via spp_approval mixin with CEL-based routing rules. Supports approve/reject/partial/revision. | spp_cel_domain | Workflow routes requests according to hierarchy and role; supports approve/reject/partial. | Models Ready |  | 1. Approval definitions created in spp_drims_sl/data/approval_config.xml: - Fast-Track: life_threatening priority (0 SLA, single manager approval) - Standard: <100k LKR (1 day SLA, single approver) - Medium: 100k-500k LKR (2 day SLA, 2-tier: District → Provincial) - Large: >500k LKR (3 day SLA, 3-tier: District → Provincial → National DMC) 2. CEL domain expressions route by priority_code_id.code and total_value 3. Multi-tier definitions use spp.approval.tier with group/user approvers 4. SLA tracking enabled via sla_days and sla_hours fields | What are the specific approval thresholds? Value-based? Item-type based? Geographic? Approval thresholds by quantity/value? Auto-approve below X?
WF-03 | Request & Approval Workflow | Automatic notifications/alerts for pending approvals or low-stock items. | MVP | 3.3.c / p1-2 | spp_alerts + spp_drims.alert | Yes | Notifications via mail.thread + spp.alert: • Approval pending: Odoo mail.activity assigned to approvers • SLA tracking: sla_status computed field (on_time/at_risk/breached) • SLA breach auto-creates alert via _check_sla_status cron • Configurable thresholds: drims.sla.hours.critical (4), high (8), routine (24), low (48) • Warning threshold at 75% elapsed (drims.sla.warning_threshold) • Alert action links: View Request button on SLA alerts • Low stock alerts: View Stock, Request Transfer buttons • Expiry alerts: View Lot, Dispose Expired buttons | Extend/Customize | Alert engine implemented for low stock, expiry, and SLA warnings/breaches via spp.drims.alert cron jobs. Thresholds are currently hardcoded in spp_drims/models/alert.py (e.g., low stock = 50% of outstanding need; expiry warning = 30 days; priority bands). spp_studio_drims provides configuration settings but is not wired into the DRIMS alert engine yet. | spp_alerts, mail | Approvers receive alerts; low-stock thresholds trigger notifications. | Models Ready | 2025-12-29: Support Yes→Partial and Status Done→In build — thresholds are hardcoded in spp_drims/models/alert.py; matrix previously claimed configurable system parameters. | 1. Alert thresholds are now configurable via Settings UI: - Low stock threshold: drims.alerts.low_stock_threshold_pct (default 50%) - Expiry warning: drims.alerts.expiry_warning_days (default 30) - Expiry critical: drims.alerts.expiry_critical_days (default 7) - Approval SLA by priority: drims.sla.hours.critical/high/routine/low - Delivery SLA: drims.delivery_sla.warning_days/critical_days/escalate_days 2. spp_drims module owns parameters (drims.* prefix) and provides helper methods 3. spp_studio_drims module provides Settings UI (DRIMS → Configuration → Alert Settings) 4. Per-incident threshold overrides available on spp.hazard.incident form | What notification channels? Email, SMS, in-app? Currently email + in-app activity. Confirm: Should thresholds be configurable via spp_studio_drims (recommended) or remain hardcoded defaults? What are the target low-stock % and expiry warning days?
DIST-01 | Issuance/Distribution/Return | Issue approved items from warehouses/stores with digital acknowledgement. | MVP | 3.4.a / p1 | stock.picking (drims_type=request_dispatch) | Yes | Issue via stock.picking with DRIMS tracking: • Request allocation creates reserved moves (FEFO) • Create Dispatch action generates outbound picking • Picking shows linked request, beneficiary area, incident • waybill_template.xml provides printable dispatch document • Print Waybill button on dispatch picking header • Waybill includes: items, quantities, signatures, incident details • Picking validation triggers DRIMS state updates | Configure | Dispatch pickings from warehouse with POD (proof of delivery) fields: receiver name, title, confirmation status. | stock | Issuance records who issued/received, date, warehouse, item lines; acknowledgement captured. | Models Ready |  | 1. Configure waybill number sequence 2. Set up POD fields: receiver_name, receiver_title, signature (if needed) 3. Configure transport mode vocabulary 4. Set up waybill report template NEEDED: Complete scenario from request to dispatch picking. | Is digital signature capture required? Currently text fields for receiver info.
DIST-02 | Issuance/Distribution/Return | Record distribution to affected populations (qty, location, beneficiary details where required). | MVP | 3.4.b / p1 | stock.picking + beneficiary fields | Partial | Beneficiary tracking on stock.picking: • beneficiary_area_id: distribution location • beneficiary_count: number of people served • distribution_type: individual/household/group • Aggregate reporting available via pivot views • Individual beneficiary registration: Phase 2 (OpenSPP registry) | Extend/Customize | Beneficiary tracking fields exist on stock.picking (beneficiary_area_id, beneficiary_count, distribution_type_id) and dispatch pickings link back to DRIMS requests, but these fields are not currently shown in spp_drims views; data capture and reporting need view updates. | spp_area | Distribution record links to issue; captures location, qty, beneficiary counts/details if enabled. | In build | 2025-12-29: Support Yes→Partial and Status Done→In build — fields exist in code but are not exposed in current DRIMS UI views. | 1. Add beneficiary fields to dispatch picking list/form views 2. Configure distribution_type vocabulary codes 3. Add validation rules for beneficiary_count (required/optional depending on distribution type) | Should individual beneficiary records be created? Currently aggregate count only. Is demographic breakdown needed (age, gender)?
DIST-03 | Issuance/Distribution/Return | Return/reuse management for non-consumables (tents, tools, equipment). | MVP | 3.4.c / p1 | spp_drims (spp.drims.return in spp_drims/models/returns.py) | Yes | spp.drims.return model for non-consumables: • Links to original dispatch picking • Line items with quantity returned and condition • States: draft → confirmed → received → inspected → restocked • Condition-based disposition (new/used_good → restock, damaged → repair/quarantine, other → dispose) • Auto-suggestion: disposition computed from condition with manual override • Good items restocked; damaged items can be quarantined or disposed • Return reason vocabulary: unused, excess, damaged, end_of_use • Create Return wizard for partial returns from dispatch | Configure | Return management for non-consumables with workflow: draft → confirmed → received → inspected → restocked. Tracks condition. | stock | Return transactions update stock and maintain history of issued vs returned items. | Models Ready | 2025-12-29: Clarified feature reference — model is spp.drims.return; implementation is in spp_drims/models/returns.py (not return.py). | 1. Configure return reason vocabulary (unused, excess, damaged, wrong_item) 2. Configure condition vocabulary for inspection (good, repairable, unusable) 3. Set up return workflow: draft → confirmed → received → inspected → restocked NEEDED: Demo return from completed dispatch. | What happens to damaged/unusable returns? Write-off workflow needed?
DIST-04 | Issuance/Distribution/Return | Consumption recording for consumable items. | MVP | 3.4.d / p1 | stock.picking (distribution) | Yes | Consumption tracked via picking completion: • Distribution picking marks items as consumed • No return expected for consumables • Audit trail via mail.tracking and spp_audit • Partial consumption: future enhancement for waste tracking | Configure | Consumable distribution tracked via picking completion. Full audit trail via spp_audit. | spp_audit | Consumable issues can be marked consumed/fully distributed with audit trail. | Models Ready |  | 1. Distribution picking completion marks items as consumed 2. Configure audit logging for distribution records 3. Consumables use product type 'consu' (vs 'product' for stockable) NEEDED: Demo consumption records. | Is partial consumption tracking needed? E.g., 100 units distributed, 80 consumed, 20 wasted?
RPT-01 | Dashboard & Reporting | Executive dashboard: stock by category & location; incoming vs distributed vs remaining; pending requests; deployment map; low stock alerts. | MVP | 3.5.a-f / p2 | spp_drims dashboard | Partial | Incident dashboard with KPIs and actions: • Stat buttons: donations, requests, alerts, returns • Real-time computed KPIs: drims_stock_value, drims_distributed_value • Searchpanel filtering by incident • 4W Coordination Report wizard (spp.drims.report.4w.wizard): - Generates pivot/graph views for humanitarian coordination - Who: Organizations by role (requester_id) - What: OCHA/IASC clusters (cluster_id, 11 sectors) - Where: Geographic areas (destination_area_id) - When: Date range filters • Graph views: request status pie, donation trend line, return status pie • Pivot views: request analysis, donation analysis, return analysis | Extend/Customize | Implemented: incident-based DRIMS dashboard (drims_dashboard_action) with donation/request KPIs and stock/distributed values via stored computed fields on spp.hazard.incident. Implemented: alerts page (spp.drims.alert) with low-stock/expiry/SLA alerts. Not implemented: total stock quantity KPI, stock-by-category chart, deployment map (no spp_gis dependency/integration), beneficiaries-served KPI, and a consolidated executive dashboard page with all widgets. | spp_hazard | Dashboard KPIs/charts match defined scope and update in near-real time. | In analysis | 2025-12-29: Support Yes→Partial and Status Done→In analysis — current DRIMS dashboard is incident KPI-based; category chart/map/beneficiary KPIs are not implemented out-of-the-box. | 1. Use DRIMS → Dashboard (spp_drims/views/dashboard_views.xml) to view incidents with KPIs (donations/requests counts, donation value, stock value, distributed value) 2. Use graph/pivot views on Donations/Requests/Returns actions for charts (not embedded into the incident dashboard) 3. Missing for scope: total stock quantity KPI; stock-by-category chart; beneficiaries-served KPI/aggregation 4. Deployment map requires integrating spp_gis and adding warehouse/agency geo layers (not in spp_drims depends today) 5. Alerts: ensure DRIMS cron jobs are enabled; expiry alerts require product_expiry module | What refresh rate for dashboard? KPIs are computed on-demand with caching.
RPT-02 | Dashboard & Reporting | Standard and customizable reports: stock summary, distribution logs, audit trails, etc. | MVP | 3.5.g / p2 | Odoo reports + pivot views | Yes | Odoo reporting engine + pivot/graph views: • Waybill PDF report with signatures • Pivot views for stock analysis by category/warehouse • Export to Excel/CSV from any list view • Custom report templates via QWeb • BI integration via standard Odoo mechanisms | Configure | Standard reports via Odoo reporting engine. Pivot views for stock analysis. Export to Excel/PDF supported. |  | Users can run/export standard reports; report templates configurable. | Done |  | 1. Use Odoo pivot views for ad-hoc analysis 2. Configure report templates for standard reports 3. Enable Excel/PDF export on list views 4. Set up scheduled report delivery if needed | What specific report templates needed? Stock summary, distribution log, audit trail formats?
SEC-01 | Roles & Access Control | User roles: Super Admin, Warehouse Manager, Field Officer, Approver, Viewer (leadership), Auditor, etc. | MVP | 3.6.a / p2 | spp_security + spp_drims groups | Yes | Role-based access via Odoo groups: • Viewer: read-only access to all DRIMS records • Officer: create requests, view donations • Manager: full access, configure settings • Approver: approve/reject requests • Inherits from spp_security base groups | Configure | DRIMS roles: Viewer, Officer, Manager + warehouse-specific. Maps to: Super Admin=SPP Admin, Warehouse Manager=Officer+Warehouse, etc. | spp_security | Role list implemented; permissions enforced by role. | Models Ready |  | 1. Demo users created in spp_drims_sl/data/demo_users.xml: - 1 Super Admin (DMC Administrator) - 2 Warehouse Managers (Colombo, Kandy) - 3 Approvers (National, Western Province, Central Province) - 4 Field Officers (Colombo, Gampaha, Kandy, Galle districts) - 2 Viewers (Secretary, Director) 2. Users mapped to Odoo groups: - Super Admin: base.group_system + spp_drims.group_drims_manager - Warehouse: spp_drims.group_drims_manager + stock.group_stock_manager - Approver: spp_drims.group_drims_approver - Field Officer: spp_drims.group_drims_officer - Viewer: spp_drims.group_drims_viewer 3. All users use @drims.gov.lk login domain with 'demo' password | Are roles warehouse-specific? E.g., Warehouse Manager for Colombo only? Specific SL agency/department names for users?
SEC-02 | Roles & Access Control | Role-based access control and audit logging. | MVP | 3.6.b / p2 | spp_audit + mail.tracking | Yes | Full audit trail via spp_audit + mail.thread: • spp.audit.log records all CRUD with old/new values • mail.tracking on DRIMS models shows field changes • User, timestamp, and action recorded • Chatter shows chronological activity feed • Export audit logs for compliance | Configure | Full audit logging via spp_audit for critical models (donations, requests, returns). Mail tracking for field changes. | spp_audit | All critical actions logged with who/when/what before/after values. | Done |  | 1. Enable spp_audit module 2. Configure audit rules for DRIMS models (donation, request, return) 3. Set fields_to_log for each model 4. Configure audit log retention period
MDM-01 | Master Data | Item master, warehouse/location master, agency/department master, user management. | MVP | 3.7.a / p2 | Odoo core masters + spp_drims_sl | Yes | Odoo core masters + DRIMS extensions: • Products: DRIMS → Inventory → Products • Categories: DRIMS → Inventory → Product Categories • Warehouses: DRIMS → Inventory → Warehouses • Agencies: res.partner with area linkage • Users: res.users with DRIMS role groups | Configure | Product master (product.product), warehouse (stock.warehouse), agency (res.partner), users (res.users). spp_drims_sl preloads SL-specific data. |  | Admins can CRUD masters; validations prevent duplicates; change history retained. | Models Ready |  | 1. Sample products created in spp_drims_sl/data/products.xml (25+ items): - Food: Rice 5kg, Dhal 1kg, Sugar 1kg, Biscuits, Canned Fish, Milk Powder - Water: 1.5L bottles, 1000L storage tanks - Medical: First Aid Kit, Paracetamol, ORS sachets - Hygiene: Soap, Toothpaste, Sanitary Pads, Buckets - Shelter: Family tents, Tarpaulins, Blankets, Sleeping mats - Equipment: LED Torch, Rope, Two-way Radio, Cooking set, Stove 2. Products use type='consu' + is_storable=True for Odoo 19 compatibility 3. Perishables have lot tracking + expiry dates configured 4. LKR prices set as standard_price for inventory valuation 5. Automatically loaded with product_categories on install | What is the master data governance process? Who can create/modify? Get actual DMC supplier list? Standard relief item codes?
DM-01 | Data/Traceability | Batch and expiry tracking for medicines/food. | MVP | 7.2.c / p4 | stock.lot + product_expiry | Yes | stock.lot + product_expiry module: • Lot tracking enabled per product (tracking='lot') • Expiry date on stock.lot via product_expiry • Lots accessible: DRIMS → Inventory → Lots & Batches • Near-expiry alerts via _cron_check_expiry • FEFO allocation supported for dispatch | Configure | Lot tracking with expiry dates via product_expiry module. Near-expiry alerts via spp_drims.alert cron job. | product_expiry | System can store batch number and expiry for relevant items and report near-expiry. | Models Ready | 2025-12-29: Clarified configuration — expiry alerts require product_expiry and the 30-day threshold is currently hardcoded in spp_drims/models/alert.py. | 1. product_expiry module added to spp_drims_sl dependencies 2. Products in spp_drims_sl/data/products.xml configured for tracking: - tracking='lot' for perishables (food, medicine) - tracking='none' for durable goods (tents, equipment) - use_expiration_date=True for items requiring expiry - expiration_time set in days (90-730 based on item type) 3. DRIMS → Inventory → Lots & Batches menu available via action_drims_lot 4. Expiry warnings configurable via product_expiry module settings 5. Lot-tracked products require lot selection during stock operations | Is FEFO (First Expiry First Out) required for dispatch? Odoo supports this.
DM-02 | Data/Traceability | Full traceability: Donor → Warehouse → Request → Issue → Distribution/Return. | MVP | 7.2.d / p4 | spp_drims relations + stock moves | Yes | Linked records from donor to distribution: • donation.id → donation_line → stock.move • request.id → request_line → stock.move • picking.drims_donation_id / drims_request_id • incident_id on all DRIMS records • Stock moves link to source/destination locations | Configure | Full chain: donation → donation_line → stock_move → picking → request → request_line. All linked via foreign keys. |  | User can drill down any stock movement to donor source and final distribution/return. | Models Ready |  | 1. Ensure all models link correctly: donation → donation_line → stock_move → picking request → request_line → stock_move → picking return → return_line → picking 2. Use drilldown actions on smart buttons NEEDED: Complete demo scenario from donation to distribution.
DM-03 | Data/Traceability | Stock balances maintained per item per warehouse; one item may exist across multiple warehouses. | MVP | 7.2.a-b / p4 | stock.quant per warehouse | Yes | stock.quant maintains per-location balances: • One quant per product/location/lot combination • quantity and reserved_quantity fields • Multi-warehouse view via Stock On Hand menu • Group by warehouse for location breakdown • Real-time updates on every transaction | Configure | Odoo stock_quant maintains balance per product per location (warehouse). Multi-warehouse supported. | stock | Stock view supports filtering by warehouse and consolidated views. | Models Ready |  | 1. Configure warehouse locations (stock.location) 2. Enable multi-warehouse in inventory settings 3. Set up inter-warehouse transfer routes if needed NEEDED: Stock quantities distributed across warehouses.
DM-04 | Data/Traceability | Stock updated after receive/issue/return via triggers or application logic. | MVP | 7.2.a / p4 | stock module | Yes | Odoo ORM transaction handling: • Stock moves validated atomically • Database transactions prevent partial updates • Reservation system prevents overselling • Concurrent access handled by PostgreSQL • Negative stock prevention via stock rules | Configure | Atomic transactions via Odoo ORM. Negative stock prevention via reservation. Concurrency handled by database locks. | stock | No negative stock; transactions are atomic; stock updates consistent under concurrency. | Models Ready |  | 1. Odoo handles concurrency via database transactions 2. Configure reservation rules if needed 3. Negative stock is prevented by default Works automatically once products/stock exist.
DASH-01 | Executive Dashboard | Top summary cards: total items, total value (if cost tracked), active requests, low stock, near expiry (30d), beneficiaries served (30d). | MVP | 8.a / p4 | spp_drims.hazard_incident computed fields | Partial | Incident KPI stat buttons on dashboard: • drims_donation_count, drims_donation_value • drims_request_count, drims_request_pending • drims_stock_value (sum of qty × price) • drims_distributed_value • drims_alert_count, drims_critical_alert_count Missing: total units count, beneficiaries_served_30d | Extend/Customize | KPIs: drims_donation_count/value, drims_request_count/pending, drims_stock_value, drims_distributed_value, drims_alert_count/critical. NOTE: beneficiaries_served_30d aggregation NOT implemented. Need to add computed field. | spp_hazard | Dashboard shows KPI cards; each definition aligns with scope. | In build | 2025-12-29: Status Done→In build — row notes missing beneficiaries_served_30d (and total stock quantity) KPI implementation. | 1. KPI computed fields on spp.hazard.incident: - drims_donation_count, drims_donation_value - drims_request_count, drims_request_pending - drims_stock_value, drims_distributed_value - drims_alert_count, drims_critical_alert_count 2. Configure cache refresh frequency (default 30 min) | Is beneficiaries_served_30d KPI implemented? Need to add computed field aggregating distribution beneficiary_count. CONFIRM: Need to implement drims_beneficiaries_served_30d computed field on incident.
DASH-02 | Executive Dashboard | Stock overview by category (bar/donut) showing quantity and % of total stock. | MVP | 8.b / p4 | Graph view + pivot | Partial | Graph views available but not embedded: • Donation trend: line chart by date • Request status: pie chart by approval_state • Returns by state: pie chart Stock by category bar chart: NOT IMPLEMENTED Requires new graph view on stock.quant grouped by categ_id | Extend/Customize | Graph views exist for donations (line), requests (pie), returns (pie). Stock by category bar/donut NOT implemented. Need to create. |  | Chart updates with filters and displays both absolute and percent values. | In build |  | 1. Create graph view definition with type='bar' or type='pie' 2. Group by product.categ_id 3. Measure by quantity or value 4. Add to dashboard action view_mode | Should chart show quantity, value, or both? Percentage calculation needs custom compute.
DASH-03 | Executive Dashboard | Real-time stock map with color-coded warehouses and drill-down to top items. | Future | 8.c / p4 | spp_gis + stock.warehouse | No | GIS integration NOT IMPLEMENTED: • spp_gis module provides PostGIS, map views, layers • NOT in spp_drims dependencies • Phase 2: Add spp_gis to depends • Phase 2: Create warehouse GIS data layer • Phase 2: Color-code by stock levels | Build New | spp_gis exists but NOT integrated with DRIMS. No GIS data layer for warehouses. Need to add spp_gis dependency and create warehouse map layer. | spp_gis, stock | Map view with warehouse markers and drilldown; requires GIS/location data. | In analysis |  | 1. Install spp_gis module with PostGIS 2. Add geo coordinates to warehouses (via area_id or direct fields) 3. Create GIS data layer for warehouses with stock quantity color coding 4. Configure map base layer (OSM recommended) | What color coding scheme for stock levels? Red/yellow/green based on thresholds?
DASH-04 | Executive Dashboard | Request status summary (pie): Pending, Approved, Partially Issued, Rejected, Completed. | MVP | 8.d / p4 | Graph view (pie) | Partial | Request status pie chart EXISTS: • spp_drims_request_view_graph in request_views.xml • type="pie" grouped by approval_state • Accessible via DRIMS → Requests → Graph view • NOT embedded in dashboard - requires navigation • Embed via dashboard customization if needed | Extend/Customize | Graph view already implemented on spp.drims.request (spp_drims_request_view_graph in spp_drims/views/request_views.xml) showing approval_state distribution (type=pie). Not embedded into the incident dashboard; embed/compose only if the executive dashboard requires it. |  | Chart matches request lifecycle states and counts accurately. | In build | 2025-12-29: Corrected notes/config — request status pie graph view already exists in spp_drims/views/request_views.xml. 2025-12-29: Added Open Question to clarify remaining scope/acceptance. | 1. Use DRIMS → Requests (action_drims_request) → Graph view 2. Existing graph view: spp_drims_request_view_graph (type=pie, group by approval_state) 3. If required inside a single dashboard page: extend dashboard composition to embed the graph or create a dedicated dashboard page | Should this chart be embedded into the executive dashboard page, or is the Requests graph view sufficient?
DASH-05 | Executive Dashboard | Latest 10 pending/high-priority requests table with actions (view/approve). | MVP | 8.e / p4 | List view with filters | Partial | Pending requests list EXISTS: • DRIMS → Operations → Pending Approval menu • Filtered to approval_state in ('pending','draft') • Sorted by priority, date_needed • Bulk approve wizard available • 'Latest 10' limit not enforced - shows all pending | Extend/Customize | Pending Approval menu/action exists (action_pending_drims_requests) with filters and approver actions, but there is no embedded dashboard table limited to the latest 10 records out-of-the-box. |  | Table shows 10 most recent matching criteria; actions respect permissions. | In build | 2025-12-29: Support Yes→Partial — pending requests list exists, but 'latest 10' embedded dashboard table is not implemented out-of-the-box. | 1. Use DRIMS → Pending Approval for a filtered request list 2. If a dashboard widget is required: create/extend a dashboard view to embed a list and enforce a limit/sort (latest 10) | Is 'latest 10' strict (enforced limit=10), or is default filtering/sorting in the Requests list acceptable?
DASH-06 | Executive Dashboard | Deployed teams & agencies view with district drilldown to contacts. | Future | 8.f / p4 | res.partner + spp_service_points | Partial | Agency/team tracking PARTIAL: • Agencies: res.partner with area_id • spp_drims_sl preloads SL agencies • Team concept NOT modeled (need custom model) • Map view: Phase 2 via spp_gis • Contact drilldown via partner form | Extend/Customize | Agencies tracked in res.partner. Teams require custom model or extension. Map view needs GIS. |  | Leaders can view team counts per district and contact details. | In build |  | 1. Create res.partner tree view filtered by is_agency 2. Group by area_id for district breakdown 3. Add drilldown to contacts within agency 4. (Phase 2) Add GIS map layer | What constitutes a 'team' vs 'agency'? Need data model clarification.
DASH-07 | Executive Dashboard | Recent activity feed (receipts, issues, approvals, alerts). | MVP | 8.g / p4 | mail.activity + chatter | Yes | Activity feed via mail.thread: • All DRIMS models inherit mail.thread • Chatter shows creates, updates, approvals • Alert notifications via mail.activity • Per-record activity, not combined feed • Combined feed: use Odoo Discuss or custom widget | Configure | Activity feed via mail.thread inherited on all DRIMS models. Shows receipts, issues, approvals, alerts. | mail | Activity feed shows latest events with links to records. | Done |  | 1. mail.thread inheritance provides activity feed on all DRIMS models 2. Configure mail templates for key actions 3. Set up mail.activity types for approvals, alerts 4. Chatter shows chronological feed
DASH-08 | Executive Dashboard | Quick filters: disaster event selector; province/district; date range (24h/7d/30d/custom). | MVP | 9.a-c / p4-5 | res.users.drims_default_incident_id + spp_hazard (spp.hazard.incident) | Partial | Incident selector on user preferences: • drims_default_incident_id on res.users • Searchpanel on all views for incident filter • Quick switch: requires custom header widget • Multi-incident view supported via removing filter | Extend/Customize | User default incident field exists on res.users (drims_default_incident_id), but DRIMS actions/views do not automatically filter records by it. Currently it mainly supports defaulting incident_id when opening actions from an incident context. | spp_hazard | Filters affect dashboard data consistently across widgets. | In build | 2025-12-29: Support Yes→Partial — drims_default_incident_id exists but is not used to auto-filter all DRIMS views/actions. 2025-12-29: Clarified feature reference — hazard incident model is spp.hazard.incident (module spp_hazard), not spp_hazard.incident. | 1. Configure res.users.drims_default_incident_id (already available) 2. If required as a global incident selector: propagate user default into action contexts/default_get and/or add search defaults in relevant views | Should users be able to view multiple incidents simultaneously? Currently single-incident focus.
DASH-09 | Additional Pages | Stock detail dashboard with search, filters, export. | MVP | 10.a / p5 | spp_area searchpanel | Partial | Area hierarchy exists but not as filter: • spp_area provides province/district/DS/GN • Not integrated as cascading filter in DRIMS • Phase 2: Add area searchpanel to DRIMS views • Can filter by area_id in search view | Extend/Customize | Area hierarchy exists in spp_area and incidents link to affected areas, but DRIMS dashboard/actions do not provide a province/district cascading filter/searchpanel out-of-the-box. | spp_area | Users can search/filter inventory and export results. | In build | 2025-12-29: Support Yes→Partial — province/district filtering requires extending DRIMS search views (not present out-of-the-box). 2025-12-29: Added Open Question to clarify remaining scope/acceptance. | 1. Configure area hierarchy (province → district → DS → GN) in spp_area 2. Extend relevant DRIMS search views to add area-based filters/searchpanel (incident areas, request destination_area_id, etc.) 3. Implement cascading behavior if required (parent_id-based domain) | Which 'stock detail dashboard' is required: incident-linked warehouses only, or global stock.quant? Are exports needed for all roles?
DASH-10 | Additional Pages | Request management page with advanced filters and bulk approval. | MVP | 10.b / p5 | Odoo date filters | Yes | Standard Odoo date filters: • Group by date fields in search views • Custom range via date picker • Preset filters (24h/7d/30d): NOT out-of-box • Phase 2: Add preset date filter definitions | Configure | Standard Odoo date filters: today, last 7 days, last 30 days, custom range. Works on all views. |  | Approvers can filter requests and bulk approve where policy allows. | Done |  | 1. Standard Odoo date filters in search view 2. Add filter presets: Today, Last 7 days, Last 30 days, This month 3. Custom date range via date picker
DASH-11 | Additional Pages | Distribution reports: beneficiary reach by district/category. | MVP | 10.c / p5 | stock.quant list view | Partial | Pivot/graph views for distribution: • beneficiary_count on stock.picking • Pivot: area × category × beneficiary_count • Export to Excel for external analysis • Custom PDF report template: Phase 2 | Extend/Customize | No dedicated distribution report views today. Beneficiary tracking fields exist on stock.picking (DRIMS extension) but are not exposed in spp_drims views, and there is no incident/district/category aggregation yet. | stock | Reports show beneficiary metrics with breakdowns and export. | In analysis | 2025-12-29: Support Yes→Partial — beneficiary fields exist in code but are not surfaced in UI and no aggregation/report views exist out-of-the-box. | 1. Add beneficiary fields to dispatch picking views 2. Create pivot/graph views grouped by beneficiary_area_id and product category 3. Optional: add incident-level computed KPI(s) for beneficiaries served | Do distribution reports need beneficiary reach by district only, or also by product category/value and demographic breakdown?
DASH-12 | Additional Pages | Expiry & low stock alerts page. | MVP | 10.d / p5 | spp_drims.alert + spp_alerts | Yes | spp.drims.alert list with filters: • DRIMS → Operations → Alerts menu • Filter by type: low_stock, expiry, sla_breach • Filter by priority: critical, high, medium, low • Filter by state: active, acknowledged, resolved • Actions: Acknowledge, Resolve, View related | Configure | Alerts page implemented via spp.drims.alert (inherits spp.alert) with list/form/search views and DRIMS menu. Cron jobs generate low-stock/expiry/SLA alerts. Thresholds are currently hardcoded unless integrating spp_studio_drims. | spp_alerts, spp_drims | Dedicated view lists near-expiry and low-stock items with thresholds. | Done | 2025-12-29: Corrected feature/notes — DASH-12 is the Alerts page (spp.drims.alert), not request management. | 1. Use DRIMS → Operations → Alerts (action_spp_drims_alert) 2. Ensure scheduled actions from spp_drims/data/ir_cron.xml are enabled 3. Optional: install product_expiry to enable expiry alerts 4. Alert thresholds configurable via DRIMS → Configuration → Alert Settings (spp_studio_drims) 5. Per-incident threshold overrides available for custom SLA/expiry values | Confirm whether expiry alerts are required (requires product_expiry) and whether alert thresholds should be configurable via spp_studio_drims.
DASH-13 | Additional Pages | Agency & team directory page with contact & deployment map. | Future | 10.e / p5 | Odoo reports + BI | Partial | Agency directory via res.partner: • Filter: is_company=True or partner.category • Area grouping via area_id • Contact fields: phone, email, contact_person • Deployment map: Phase 2 via spp_gis • spp_drims_sl preloads SL government agencies | Extend/Customize | Distribution reports need custom templates. Beneficiary reach by district available via pivot. Category breakdown needs report. |  | Directory view includes optional map when location is available. | In build |  | 1. Pivot view: rows=beneficiary_area_id, columns=product.categ_id, measure=beneficiary_count 2. Date range filter for reporting period 3. Export to Excel for further analysis 4. (Phase 2) Custom report templates | What specific report formats needed? PDF templates? Excel with charts?
DEL-01 | Deliverables | Web-based inventory management system (responsive design). | MVP | 5.a / p2 | spp_drims.alert views | Yes | Web-based responsive Odoo UI: • Odoo 19 web client is responsive • Works on desktop, tablet browsers • Mobile optimization varies by view • PWA support: Phase 2 • Native mobile app: not included | Configure | Dedicated alert page with filters by type, priority, state. Expiry and low stock alerts auto-generated by cron. | spp_alerts | System works on desktop/tablet/mobile browsers with usable layout. | Done |  | 1. spp.drims.alert list view with filters 2. Filter by alert_type: low_stock, expiry, sla_breach 3. Priority highlighting: critical=red, high=orange 4. Actions: Acknowledge, Resolve, Dismiss
DEL-02 | Deliverables | Centralized database with secure backup. | MVP | 5.b / p2 | res.partner + spp_service_points | Partial | PostgreSQL database with backup: • Standard PostgreSQL deployment • Backup via pg_dump or container volumes • Hosting: customer responsibility • Doodba provides backup scripts • RPO/RTO per hosting configuration | Extend/Customize | Agency directory via res.partner. Deployment map requires GIS integration (Phase 2). |  | Database backups scheduled; restore tested; access controlled. | In build | 2025-12-29: Added Open Question to clarify remaining scope/acceptance. | 1. res.partner list view with domain [('is_agency','=',True)] 2. Columns: name, area, contact_person, phone, email 3. Search by area hierarchy 4. (Phase 2) Map view via spp_gis | What are the backup/restore requirements (RPO/RTO), retention period, and hosting environment (on-prem vs cloud)?
DEL-03 | Deliverables | SOP and user manual; admin and end-user training. | MVP | 5.d-e / p2 |  | Unknown | Documentation deliverable - TBD: • SOP templates can be provided • User manual: content depends on customizations • Training: scope to be defined • Admin guide: Odoo standard + DRIMS specifics | TBD |  |  | Docs delivered; training sessions conducted; materials stored. | In analysis
DEL-04 | Deliverables | 3–6 months of post-go-live support. | MVP | 5.f / p2 |  | Unknown | Support deliverable - TBD: • Support period to be defined in contract • Bug fixes during warranty period • Enhancement requests separate • SLA terms to be agreed | TBD |  |  | Support plan defined with SLAs and handover completed. | In analysis
NFR-01 | Assumptions/Constraints | Internet connectivity available at warehouses/coordination centers. | TBD | 6.a / p2 |  | Unknown | Assumption - connectivity: • Odoo requires internet for web access • Offline mode: not natively supported • Phase 2: Consider offline-first PWA • Local deployment possible for LAN-only | TBD |  |  | Connectivity requirements documented; offline process defined if outages occur. | In analysis
NFR-02 | Assumptions/Constraints | Must comply with government data security and privacy standards. | MVP | 7.a / p2 |  | Unknown | Assumption - compliance: • Odoo provides data protection features • Audit logging via spp_audit • Role-based access control • SSL/TLS for transport security • Specific compliance: review with customer | TBD |  |  | Security controls documented; access logs and data protection meet standards. | In analysis
NFR-03 | Assumptions/Constraints | Barcoding/physical tagging handled separately (if required). | TBD | 6.c / p2 |  | Unknown | Barcode/tagging separate: • Product barcodes supported • Lot barcodes supported • Physical label printing: via Odoo reports • Handheld scanning: Phase 2 or Enterprise • RFID: not supported | TBD |  |  | Operational process defined for printing/attaching codes; system can store code values. | In analysis

## Lists
SupportStatus | Yes | Partial | No | Unknown
Approach | Configure | Extend/Customize | Integrate | Build New | TBD
Priority | MVP | Phase 2 | Future | Out of Scope | TBD
ImplementationStatus | Not started | In analysis | In build | Blocked | Done | TBD

## Data Model
Entity/Table | Key columns (from spec) | Purpose (from spec) | OpenSPP equivalent | OpenSPP support? | Approach | Notes | Source (section/page) | Configuration Details | Open Questions
users | user_id (PK), username, password_hash, full_name, phone, email, role_id (FK), agency_id (FK), district_id, is_active | All system users (admin, warehouse manager, field officer, leader) | res.users | Yes | Configure | Odoo core user model. DRIMS adds drims_default_incident_id, drims_default_warehouse_id, drims_area_ids, drims_warehouse_ids fields. | 7.1 / p2-3 | 1. Standard res.users with DRIMS fields added via extension 2. Configure drims_default_incident_id for user context 3. Set drims_area_ids for geographic jurisdiction 4. Assign to appropriate security groups | Should users have multiple jurisdiction areas? Currently M2M supported.
roles | role_id (PK), role_name (Super Admin, Warehouse Manager, Field Officer, Approver, Leader, Auditor) | Role-based access control | res.groups (spp_security + spp_drims) | Yes | Configure | Role-based via Odoo groups. spp_drims defines: Viewer, Officer, Manager. Inherits from spp_security base groups. | 7.1 / p3 | 1. Groups defined in spp_drims/security/groups.xml 2. Hierarchy: Viewer < Officer < Manager < Admin 3. Configure implied_ids for group inheritance | Are role names customizable per deployment? E.g., 'District Coordinator' vs 'Field Officer'?
agencies | agency_id (PK), agency_name, agency_type (Gov, NGO, Military, etc.), contact_person, phone | Government & partner agencies | res.partner (with spp_area area_id) | Yes | Configure | Agencies as res.partner companies: • is_drims_organization flag for DRIMS participants • drims_organization_role_id (vocabulary-based) • Organization roles vocabulary with 6 standard roles • Coordination modes vocabulary for incident-level settings • OCHA/IASC clusters vocabulary for 4W What dimension | 7.1 / p3 | 1. Create agencies as res.partner (is_company=True) 2. Use res.partner.category tags for agency_type (Gov/NGO/Military/etc.) 3. Set res.partner.area_id (from spp_area) for jurisdiction/location 4. spp_drims_sl preloads SL agencies in data/agencies.xml | Should agencies have a separate model or use res.partner? Currently res.partner approach.
districts | district_id (PK), district_name, province_id (FK), ds_division_id, gs_division_id | Geographic hierarchy | spp.area (hierarchy) | Yes | Configure | Full geographic hierarchy via spp_area module. Parent/child relationships for province → district → DS → GN divisions. | 7.1 / p3 | 1. Import area hierarchy via spp.area.import 2. Configure area kinds: province, district, ds_division, gn_division 3. Set parent_id relationships 4. spp_drims_sl imports from lka_adminboundaries_tabulardata.xlsx
provinces | province_id (PK), province_name | Geographic hierarchy | spp.area (kind=province) | Yes | Configure | Province level in spp.area with kind_id = province. spp_drims_sl imports all 25 SL districts + 9 provinces. | 7.1 / p3 | 1. Top-level areas with kind_id = province 2. SL has 9 provinces as top level
dsdivision | ds_division_id, ds_name | Geographic hierarchy | spp.area (kind=ds_division) | Yes | Configure | DS Division level in spp.area. Linked to district via parent_id. | 7.1 / p3 | 1. Area kind 'ds_division' under districts 2. Links to district via parent_id
gndivision | gn_division_id, dn_name | Geographic hierarchy | spp.area (kind=gn_division) | Yes | Configure | GN Division level in spp.area. Linked to DS division via parent_id. | 7.1 / p3 | 1. Area kind 'gn_division' under DS divisions 2. Lowest level of hierarchy | Is GN-level granularity needed for DRIMS? May simplify to DS level.
warehouses | warehouse_id (PK), warehouse_name, district_id (FK), location_address, manager_user_id (FK) | Storage locations | stock.warehouse + DRIMS fields | Yes | Configure | Odoo warehouse with is_drims_warehouse flag, drims_capacity, incident_ids, area_id, emergency contact fields. | 7.1 / p3 | 1. Create stock.warehouse with is_drims_warehouse=True 2. Link to area_id for location 3. Set incident_ids M2M for disaster association 4. Configure emergency_contact fields 5. spp_drims_sl preloads SL warehouses | How many warehouses expected? National, regional, mobile?
item_categories | category_id (PK), category_name (Food, Water, Medicine, Shelter, Hygiene, Equipment, etc.) | Item grouping | product.category | Yes | Configure | Standard Odoo product categories. spp_drims_sl defines: Food, Water, Medicine, Shelter, Hygiene, Equipment, Non-consumables. | 7.1 / p3 | 1. Create product.category records 2. Standard categories: Food, Water, Medicine, Shelter, Hygiene, Equipment 3. Can add subcategories as needed
items | item_id (PK), item_name, category_id (FK), unit_of_measure (pcs/kg/liter/box), is_consumable (Yes/No), shelf_life_days | Master list of all relief items | product.product + product.template | Yes | Configure | Odoo product master with UoM, is_consumable via product type (consu vs product). shelf_life via product_expiry module. | 7.1 / p3 | 1. Create product.product (or product.template) 2. Set type='product' for stockable, 'consu' for consumable 3. Configure UoM (units, kg, liters, boxes) 4. Enable tracking='lot' for lot-tracked items 5. Use product_expiry for shelf life | Is a master product catalog provided? Or items created on-the-fly?
inventory_receive | receive_id (PK), receive_date, donor_source, received_by (user_id FK), remarks | Incoming goods header | spp.drims.donation | Yes | Configure | Donation header: reference, incident_id, donor_id, source_type, warehouse_id, dates, state workflow. | 7.1 / p3 | 1. spp.drims.donation model 2. Configure donation reference sequence (DON-YYYY-NNNNN) 3. Set up source_type vocabulary 4. Link to incident and warehouse
inventory_receive_details | receive_detail_id (PK), receive_id (FK), item_id (FK), quantity_received, batch_no, expiry_date | Line items of received goods | spp.drims.donation.line | Yes | Configure | Donation line items: product_id, qty_pledged, qty_received, condition, disposition, lot_number, expiry_date. | 7.1 / p3 | 1. spp.drims.donation.line model 2. Links to donation_id and product_id 3. Stores qty_pledged, qty_received, condition, expiry_date
inventory_stock | stock_id (PK), warehouse_id (FK), item_id (FK), current_quantity, reserved_quantity | Real-time stock balance (one row per item per warehouse) | stock.quant | Yes | Configure | Odoo stock quant for real-time inventory. One record per product/location/lot with quantity + reserved_quantity. | 7.1 / p3 | 1. stock.quant is Odoo native - no configuration needed 2. One record per product/location/lot combination 3. reserved_quantity tracks allocations
requests | request_id (PK), request_no, requested_by (user_id FK), request_date, district_id (FK), status (Pending/Approved/Rejected/Partial), priority | Request header | spp.drims.request | Yes | Configure | Request header: reference, incident_id, destination_area_id, priority, dates, state, affected_population, approval fields. | 7.1 / p3 | 1. spp.drims.request model 2. Configure request reference sequence (REQ-YYYY-NNNNN) 3. Set up priority vocabulary 4. Configure approval workflow rules
request_details | req_detail_id (PK), request_id (FK), item_id (FK), quantity_requested, quantity_approved | Requested items | spp.drims.request.line | Yes | Configure | Request line items: product_id, qty_requested/approved/allocated/dispatched/delivered, fulfillment_pct. | 7.1 / p3 | 1. spp.drims.request.line model 2. Tracks qty_requested, qty_approved, qty_allocated, qty_dispatched, qty_delivered 3. Computes fulfillment_pct
issues | issue_id (PK), request_id (FK), issue_date, issued_by (user_id), warehouse_id (FK), remarks | Goods issued from warehouse | stock.picking (drims_type=request_dispatch) | Yes | Configure | Issues from warehouse via stock.picking. Links to drims_request_id. Includes waybill_number, transport details. | 7.1 / p3 | 1. stock.picking with drims_type='request_dispatch' 2. Links to drims_request_id 3. Generates waybill_number from sequence 4. Stores transport and POD fields
issue_details | issue_detail_id (PK), issue_id (FK), item_id (FK), quantity_issued | Issued items | stock.move | Yes | Configure | Stock moves link to drims_request_line_id or drims_donation_line_id for traceability. | 7.1 / p3 | 1. stock.move created automatically by picking 2. Links to drims_request_line_id for traceability 3. Quantity issued stored in quantity field
distributions | dist_id (PK), issue_id (FK), distributed_date, distributed_by (user_id), beneficiary_area, no_of_beneficiaries, remarks | Final distribution to people (only for consumables) | stock.picking (distribution fields) | Yes | Configure | Distribution to people via picking completion. beneficiary_area_id, beneficiary_count, distribution_type fields. | 7.1 / p3 | 1. stock.picking completion with distribution fields 2. beneficiary_area_id, beneficiary_count, distribution_type 3. Links back to issue/request | Is separate distribution record needed? Currently part of picking completion.
returns | return_id (PK), issue_id (FK), return_date, returned_by (user_id), warehouse_id (FK), remarks | Return of non-consumable items | spp.drims.return | Yes | Configure | Return header: incident_id, original_picking_id, warehouse_id, state workflow (draft→confirmed→received→inspected→restocked). | 7.1 / p3 | 1. spp.drims.return model 2. Configure return reference sequence (RET-YYYY-NNNNN) 3. Set up return_reason vocabulary 4. Workflow: draft → confirmed → received → inspected → restocked
return_details | ret_detail_id (PK), return_id (FK), item_id (FK), quantity_returned | Returned items | spp.drims.return.line | Yes | Configure | Return line items: product_id, quantity_dispatched (orig), quantity_returned, condition notes. | 7.1 / p3 | 1. spp.drims.return.line model 2. Stores qty_dispatched (original) and qty_returned 3. Tracks condition of returned items
audit_log | log_id (PK), user_id (FK), action_time, table_name, record_id, action (INSERT/UPDATE/DELETE), old_values, new_values | Full audit trail | spp.audit.log (spp_audit) | Yes | Configure | Full audit trail via spp_audit module. Logs all CRUD operations with user, timestamp, old/new values. JSON format. | 7.1 / p3 | 1. spp.audit.log via spp_audit module 2. Configure audit rules per model 3. Stores: user, timestamp, model, record_id, action, old/new values as JSON 4. Immutable log with retention policy | What is the required audit retention period?

## Dashboard
Component ID | Dashboard area | Widget/Report | Metric definition / fields | Priority | OpenSPP support? | OpenSPP Solution | Approach | Notes | Source (section/page) | Configuration Details | Open Questions
KPI-01 | Top Summary Cards | Total items in stock (all warehouses) | Total units and/or distinct items aggregated across warehouses (confirm definition) | MVP | Partial | PARTIAL - Value tracked, units missing: • drims_stock_value: Total monetary value (implemented) • TODO: drims_total_stock_units (sum of quantities) • TODO: drims_stock_item_count (distinct products) | Extend/Customize | No incident-level 'total units in stock' KPI field implemented. Current incident KPIs include stock value (drims_stock_value) but not total quantity/sku count. 2025-12-29: Downgraded Yes→Partial — quantity KPI not present; only stock value KPI exists. | 8.a.i / p4 | 1. Add a stored computed field on spp.hazard.incident (e.g., drims_stock_qty) aggregating stock.quant quantities across incident warehouses 2. Decide definition: total units vs distinct SKUs vs both 3. Expose KPI on DRIMS dashboard views | Definition: total units or distinct SKUs? Currently shows total units.
KPI-02 | Top Summary Cards | Total value of stock (if cost tracked) | Requires cost/valuation data; optional per scope | Future | Yes | drims_stock_value computed field on spp.hazard.incident. Sum of qty × standard_price for all stock in incident warehouses. Displayed as stat button on incident form. | Configure | drims_stock_value computed field. Sum of qty × standard_price for all stock in incident warehouses. | 8.a.ii / p4 | 1. drims_stock_value computed field 2. sum(quantity × product.standard_price) 3. Requires cost data on products Demo needs: Products with standard_price, stock quants in warehouses. | Is cost tracking mandatory? standard_price field on products.
KPI-03 | Top Summary Cards | Active requests (Pending Approval) | Count requests where status indicates pending approval | MVP | Yes | drims_request_pending computed field. Count where approval_state in ('pending', 'draft'). Displayed as stat button with click-through to request list. | Configure | drims_request_pending computed field. Count requests where approval_state in (pending, draft). | 8.a.iii / p4 | 1. drims_request_pending computed field 2. Count where approval_state in ('pending', 'draft') 3. Display as stat button with click to list view Demo needs: Sample requests in pending/draft state.
KPI-04 | Top Summary Cards | Critical/Low Stock Items | Threshold: <20% OR <3 days (needs threshold definition and baseline) | MVP | Partial | IMPLEMENTED on spp.hazard.incident: • drims_alert_count: Active + acknowledged alerts • drims_critical_alert_count: Critical priority alerts only • Displayed as stat button on incident dashboard • Links to filtered alert list view • Alert engine cron checks: low_stock, expiry, sla_breach | Extend/Customize | Low stock alert via spp_drims.alert cron. Threshold configurable in spp_studio_drims. Need dashboard card. | 8.a.iv / p4 | 1. Alert count from spp.drims.alert where type=low_stock 2. Threshold: 50% of pending request quantity (hardcoded in alert.py:160) 3. To customize threshold: modify _check_incident_stock_levels() 4. drims_alert_count and drims_critical_alert_count on incident | What defines 'low stock'? Absolute threshold or percentage of demand?
KPI-05 | Top Summary Cards | Items expired or near expiry (next 30 days) | Expiry date within next 30 days, plus already expired | MVP | Yes | Expiry alerts via _cron_check_expiry cron job. Checks stock.lot.expiration_date within 30 days. Requires product_expiry module installed. Priority: critical ≤7d, high ≤14d, medium ≤30d. | Configure | Expiry alert via _cron_check_expiry. Uses product_expiry module. 30-day threshold. Alert created for each. | 8.a.v / p4 | 1. Alert count from spp.drims.alert where type=expiry 2. _cron_check_expiry runs daily (scheduled action) 3. Threshold: 30 days (hardcoded in alert.py:208) 4. Requires product_expiry module installed 5. Priority: critical (≤7 days), high (≤14 days), medium (≤30 days)
KPI-06 | Top Summary Cards | Total beneficiaries served (last 30 days) | Sum no_of_beneficiaries from distributions in last 30 days | MVP | No | NOT IMPLEMENTED - beneficiary tracking exists but not aggregated: • beneficiary_count field exists on stock.picking • TODO: drims_beneficiaries_served computed field on incident • TODO: Filter to last 30 days from completed distributions | Build New | NOT IMPLEMENTED. beneficiary_count exists on picking but no aggregated KPI on incident. Need to add computed field summing last 30 days. | 8.a.vi / p4 | 1. Need to add computed field aggregating beneficiary_count 2. Sum from stock.picking where state=done and date in last 30 days 3. Filter by incident | Is this implemented? Need to verify computed field exists. May need to add.
CH-01 | Stock Overview | Stock by category (bar/donut) | Food/Water/Medicine/Shelter/Hygiene/Equipment/Others: quantity + % total; filterable | MVP | Partial | PARTIAL - Need graph view for stock.quant: • Stock quant list/pivot views exist (action_drims_stock_quant) • Missing: Graph view grouped by product category • TODO: Add bar/donut chart for category breakdown | Extend/Customize | NOT IMPLEMENTED. Need to create graph view for stock.quant grouped by product category. Existing graphs: donation trend (line), request status (pie), returns (pie). | 8.b / p4 | 1. Create ir.ui.view with arch type='graph' 2. <graph type='bar'> or <graph type='pie'> 3. <field name='categ_id' type='row'/> 4. <field name='quantity' type='measure'/> | Should show quantity, value, or percentage? Bar vs pie vs donut?
MAP-01 | Stock Map | Real-time stock map | Country/province/district map; color-coded warehouses; drilldown to top 10 items | Future | No | NOT IMPLEMENTED. spp_gis module exists with PostGIS backend. NOT in spp_drims depends. Phase 2: Add GIS integration, warehouse layer, color coding. | Build New | NOT IMPLEMENTED. spp_gis module exists but not integrated with DRIMS. Need to: (1) add spp_gis to depends, (2) create warehouse GIS data layer, (3) add map view. | 8.c / p4 | 1. Install spp_gis module 2. Create GIS data layer for warehouses 3. Configure color coding by stock level 4. Add popup with warehouse details and top 10 items | What map interaction needed? Click to drilldown? Hover popup?
CH-02 | Requests | Request status summary (pie) | Pending/Approved/Partially Issued/Rejected/Completed counts with filters | MVP | Yes | IMPLEMENTED: spp_drims_request_view_graph • Pie chart grouped by approval_state • Shows: Draft, Pending, Approved, Rejected distribution • Included in request action view_mode: list,kanban,graph,pivot,form • Sample data enabled for empty states | Extend/Customize | Graph view exists for request status distribution (spp_drims_request_view_graph in spp_drims/views/request_views.xml). Accessible via DRIMS → Requests → Graph view button. NOT embedded in dashboard; requires navigation. 2025-12-30: Confirmed graph type="pie" with approval_state field. | 8.d / p4 | 1. Use DRIMS → Requests → Graph view (pie) 2. Existing view: spp_drims_request_view_graph (group by approval_state) 3. If needed as a dashboard widget: compose/embed graph in a dedicated dashboard page | Should this chart be embedded into the executive dashboard page, or is the Requests graph view sufficient?
TB-01 | Requests | Latest 10 pending/high-priority requests table | Request#, Date, District, Requested By, Priority, Status, Action (View/Approve) | MVP | Partial | PARTIAL - filtered list exists, no limit: • Pending Approval menu (action_pending_drims_requests) • TODO: Create action with limit=10 and priority ordering • Or: Dashboard widget component | Extend/Customize | Pending-approval request list exists, but no embedded dashboard table limited to the latest 10 items is implemented out-of-the-box. 2025-12-29: Downgraded Yes→Partial — no out-of-box embedded 'latest 10' table. | 8.e / p4 | 1. Use DRIMS → Pending Approval for the filtered list 2. If a dashboard widget is required: embed a list with enforced limit/sort (latest 10) | Is the 'Latest 10' requirement strict (limit=10), or is a filtered list acceptable?
TEAM-01 | Teams/Agencies | Deployed teams & agencies view | Map or list: #teams per district; drilldown to agencies + contact persons | Future | No | NOT IMPLEMENTED. Agencies in res.partner with area_id. 'Team' concept not modeled. Phase 2: Define team model, GIS layer. | Build New | NOT IMPLEMENTED. Agency list available but no team tracking or map view. Need to define team model and create GIS layer. | 8.f / p4 | 1. List view of agencies with team counts 2. Group by area_id (district) 3. (Phase 2) Map visualization via spp_gis | What is a 'team'? How to count teams per agency/district?
FEED-01 | Activity | Recent activity feed | Receipts, issues, approvals, alerts (e.g., low stock, near expiry) | MVP | Yes | mail.thread on all DRIMS models. Chatter shows per-record activity. Alert notifications via mail.activity. Combined feed: use Discuss or custom widget. | Configure | Chatter/activity feed on all DRIMS models (mail.thread). Shows creates, updates, approvals. Alert notifications via mail.activity. | 8.g / p4 | 1. mail.message/mail.activity on DRIMS models 2. Chatter shows chronological feed per record 3. For cross-record feed, use activity dashboard | Is a combined activity feed across all DRIMS records needed?
FLT-01 | Filters | Disaster event selector | If multiple active disasters: selector defines scope for inventory/requests/reporting | MVP | Yes | drims_default_incident_id on res.users. Searchpanel on donations/requests/returns/alerts. User can filter by incident in any view. | Configure | Incident selector on user preferences (drims_default_incident_id). Searchpanel on all views filters by incident. | 9.a / p4-5 | 1. User preference: drims_default_incident_id 2. Selector in user preferences or header widget 3. Context key propagates to all views/actions | Can users switch incidents without going to preferences? Need quick selector.
FLT-02 | Filters | Province/District filter | Filters all widgets and reports by geography | MVP | Partial | PARTIAL - hierarchy exists, not cascading: • spp.area has parent_id hierarchy (Province > District > DS > GN) • Searchpanel on requests/donations filters by incident • TODO: Add area searchpanel with enable_counters • TODO: Consider cascading domain filter | Extend/Customize | Area hierarchy exists (spp_area) but DRIMS dashboard/actions do not include a province/district cascading filter/searchpanel out-of-the-box. 2025-12-29: Downgraded Yes→Partial — province/district filtering requires view extensions. | 9.b / p5 | 1. Configure area hierarchy in spp_area 2. Extend DRIMS search views to add area filters/searchpanel and (if required) cascading behavior | Should filtering be based on incident affected areas (incident.area_ids) or on destination areas of requests/distributions?
FLT-03 | Filters | Date range filter | Presets 24h/7d/30d/custom; applies consistently | MVP | Partial | PARTIAL - custom date picker, no presets: • Odoo date fields with calendar picker • TODO: Add search filters for common presets: - Last 24 hours, Last 7 days, Last 30 days • Add to request, donation, alert, picking search views | Extend/Customize | Hazard incident search view groups by start date but does not provide the requested preset date range filters (24h/7d/30d) out-of-the-box. 2025-12-29: Downgraded Yes→Partial — preset date-range filters are not implemented out-of-the-box. | 9.c / p5 | 1. Extend spp.hazard.incident and related DRIMS search views to add date filter presets (24h/7d/30d/custom) 2. Ensure dashboard actions use the updated search views | Do the date filters apply to incident start_date, request date_needed, stock movements, or all (separately)?
PG-01 | Menu Page | Stock detail dashboard | Full inventory list with search, filters, export | MVP | Yes | DRIMS → Inventory → Stock On Hand menu. action_drims_stock_quant filtered to DRIMS warehouses. Group by warehouse, category. Export to Excel. | Configure | stock.quant list view with search, filters by warehouse/category/product. Group by warehouse. Export button. NEW (2025-12-30): Added DRIMS → Inventory → Stock On Hand menu (action_drims_stock_quant) filtered to DRIMS warehouses. | 10.a / p5 | 1. NEW: DRIMS → Inventory → Stock On Hand (action_drims_stock_quant) 2. Domain: [('location_id.warehouse_id.is_drims_warehouse', '=', True)] 3. Group by: warehouse_id, product_categ_id 4. Export to Excel via standard Odoo export 5. Pivot view available for analysis
PG-02 | Menu Page | Request management | Advanced filters & bulk approval | MVP | Yes | DRIMS → Operations → Requests menu. List, form, kanban, graph, pivot views. bulk_approve_wizard for multi-select. Advanced search on priority, state, area. | Configure | Request list with filters + bulk_approve_wizard for multi-select approve/reject. Advanced search on priority, state, area. | 10.b / p5 | 1. Menu action for spp.drims.request 2. Include tree, form, kanban, pivot views 3. bulk_approve_wizard for batch operations Demo needs: Sample requests for bulk approval testing.
PG-03 | Menu Page | Distribution reports | Beneficiary reach by district/category | MVP | Partial | PARTIAL - pivot exists, beneficiary dimension missing: • 4W pivot view has area × requester × month • TODO: Distribution pivot with beneficiary_count measure • TODO: Group by destination_area_id, product category | Extend/Customize | Need custom report template. Pivot view available for ad-hoc analysis by area × category. | 10.c / p5 | 1. Pivot view: area × category × measure(beneficiary_count) 2. Date range filter 3. Export to Excel | What standard report templates are needed? PDF, Excel?
PG-04 | Menu Page | Expiry & low stock alerts | Dedicated alert page | MVP | Yes | DRIMS → Operations → Alerts menu. Filter by type, priority, state. Actions: Acknowledge, Resolve. Low stock + expiry auto-generated by cron. | Configure | spp.drims.alert list view with filters: type, priority, state. Actions: acknowledge, resolve. Low stock + expiry auto-generated. | 10.d / p5 | 1. Menu action for spp.drims.alert 2. Filters by type, priority, state 3. Actions: Acknowledge, Resolve Demo needs: Sample alerts (or run cron jobs after setting up stock).
PG-05 | Menu Page | Agency & team directory | Directory + optional deployment map | Future | Partial | res.partner list filtered by category. Group by area_id for district breakdown. Map view: Phase 2 via spp_gis. | Extend/Customize | Agency directory via res.partner is_agency. spp_gis provides map visualization. Need to link agencies to geo coordinates via area_id or direct lat/lng. | 10.e / p5 | 1. res.partner list with domain [('is_agency','=',True)] 2. Search by area, contact 3. (Phase 2) Map view via spp_gis | Is the directory purely contact information, or does it need deployment status + (optional) GIS map integration?

## Out of Scope - Later
Item ID | Excluded / Later item | Classification | Notes / Implications | Source (section/page)
OOS-01 | Full financial accounting or procurement modules | Out of Scope | If needed later, define procurement workflow and costing/valuation; affects KPI 'Total value'. | 4.a / p2
OOS-02 | Direct beneficiary registration and cash-transfer systems | Out of Scope | Distribution records only; not a social registry / payment platform. | 4.b / p2
OOS-03 | Offline mobile distribution app for last-mile workers | Phase 2 | Could be a separate mobile app; clarify offline mode and sync. | 4.c / p2
OOS-04 | Advanced predictive analytics or demand forecasting | Future | Would require historical data and model governance. | 4.d / p2
OOS-05 | Integration with external logistics or transportation management systems (unless specified later) | Future | Clarify interfaces if fleet/route tracking is later required. | 4.e / p2
OOS-06 | Public-facing portal for citizens | Out of Scope | Only authorized stakeholders; no citizen portal. | 4.f / p2